## Task_Page
Test Plan for A/B Test Functionality
Test Execution Start Date : 01-04-2025
Test Execution End Date : 28-04-2025
Test Executionar : Koushik Raju

1. Introduction
This test plan is designed to validate the functionality of the A/B Test feature in the app.vwo.cop web portal. / The A/B Test feature allows users to create, view, and manage A/B tests across different sections (Easy to Edit, Cross Platform Testing, and Powered by Smartstast).

2. Test Objective
The main objective of this testing is to verify that: / *The A/B Test section is accessible and functional. / *The user can interact with different sections, create A/B tests, view sample tests, and navigate smoothly within the portal. / *The buttons and interactions like Create A/B Test, View Sample Test, and section descriptions work as expected. / *All the workflows and scenarios related to section selection, navigation, error handling, and UI responsiveness are functioning correctly.

3. Scope of Testing
The scope of testing will include the following: / *Section Creation / *A/B Test creation / *UI behaviour / *Error handeling
4. Number of Test Cases = 15

5. Test Type
Functional Testing, UI Testing, Usability Testing, Error Handling

6.Test Assumptions
- User is logged in.
- The website is accessible without downtime.
- The A/B Test section is correctly implemented.

7.Pass/Fail Criteria
A test case will pass if the expected result matches the actual result. A test case will fail if there is a deviation.

## Test_Case_Details
Test Case Details

Test Execution Start Date : 01-04-2025
Test Execution End Date : 28-04-2025
Test Executionar : Koushik Raju

	Test case No	Test Case Description	Priority	Pre Condition	Status
	TC_A/B Test_01	Verify successful login and navigation to A/B Test section.	HIGH	User must be logged into the website (app.vwo.com).	Pending
	TC_A/B Test_02	Verify the "Easy to Edit" section is clickable and opens the description.	HIGH	User must be logged into the website and in the A/B Test section.	Pending
	TC_A/B Test_03	Verify the "Cross Platform Testing" section is clickable and opens the description.	MEDIUM	User must be logged into the website and in the A/B Test section.	Pending
	TC_A/B Test_04	Verify the "Powered by Smartstast" section is clickable and opens the description.	HIGH	User must be logged into the website and in the A/B Test section.	Pending
	TC_A/B Test_05	Verify the "Create A/B Test" button redirects the user to the A/B test creation page.	HIGH	User must be logged into the website and in the A/B Test section.	Pending
	TC_A/B Test_06	Verify the "View Sample Test" button opens a sample test.	HIGH	User must be logged into the website and in the A/B Test section.	Pending
	TC_A/B Test_07	Verify the user can navigate back from the A/B test creation page to the A/B Test section.	HIGH	User must be logged into the website and be in the A/B Test creation page.	Pending
	TC_A/B Test_08	Verify that the user can select only one section at a time.	HIGH	User must be logged into the website and in the A/B Test section.	Pending
	TC_A/B Test_09	Verify that the user can cancel or close the sample test view.	HIGH	User must be logged into the website and in the A/B Test section with any section selected.	Pending
	TC_A/B Test_10	Verify that "Create A/B Test" button is disabled if no sections are selected.	HIGH	User must be logged into the website and in the A/B Test section, and no section should be selected.	Pending
	TC_A/B Test_11	Verify the UI layout of the A/B Test section is responsive across different devices.	HIGH	User must be logged into the website and in the A/B Test section on a mobile, tablet, or desktop device.	Pending
	TC_A/B Test_12	Verify that the user can successfully logout after using the A/B Test section.	HIGH	User must be logged into the website and in the A/B Test section.	Pending
	TC_A/B Test_13	Verify that the A/B Test section loads within 5 seconds.	LOW	User must be logged into the website.	Pending
	TC_A/B Test_14	Verify that a user can cancel the creation of an A/B test and return to the A/B Test section.	HIGH	User must be logged into the website and in the A/B Test section with a section selected.	Pending
	TC_A/B Test_15	Verify that "View Sample Test" displays a summary of the test configuration.	HIGH	User must be logged into the website and in the A/B Test section with a section selected.	Pending

## Test_Execution&Result
Test case No	Test Case Title	Pre Condition	Steps to Execute	Expected Result	Actual Result	Status	Executed QA Name	Misc (Comments)
TC_A/B Test_01	Verify successful login and navigation to A/B Test section.	User must be logged into the website (app.vwo.com).	1. Log in to the website. / 2. Click on the A/B Test icon.	User is redirected to the A/B Test section.	User is succesfully redirected to the A/B Test section.	PASS	Koushik Raju
TC_A/B Test_02	Verify the "Easy to Edit" section is clickable and opens the description.	User must be logged into the website and in the A/B Test section.	1. Click on the A/B Test icon. / 2. Click on the "Easy to use Editor" section.	"Easy to use Editor" should opens successfully.	The "Easy to use Editor" opens successfully.	PASS	Koushik Raju
TC_A/B Test_03	Verify the "Cross Platform Testing" section is clickable and opens the description.	User must be logged into the website and in the A/B Test section.	1. Click on the A/B Test icon. / 2. Click on the "Criss Platfor Testing" section.	"Cross Platform Testing" should opens successfully.	The "Cross Platform testing" opens successfully.	PASS	Koushik Raju
TC_A/B Test_04	Verify the "Powered by Smartstast" section is clickable and opens the description.	User must be logged into the website and in the A/B Test section.	1. Click on the A/B Test icon. / 2.Click on the "Powered by Smartstast" section.	"Powered by Smartstast" should open successfully.	The "Powered bt Smartstats" opens successfully.	PASS	Koushik Raju
TC_A/B Test_05	Verify the "Create A/B Test" button redirects the user to the A/B test creation page.	User must be logged into the website and in the A/B Test section.	1. Select any section (Easy to Edit, Cross Platform Testing, Powered by Smartstast). / 2. Click on the "Create A/B Test" button.	User should be redirected to the creation page.	User succesfully redirected to the creation page.	PASS	Koushik Raju
TC_A/B Test_06	Verify the "View Sample Test" button opens a sample test.	User must be logged into the website and in the A/B Test section.	1. Select any section (Easy to Edit, Cross Platform Testing, Powered by Smartstast). / 2. Click on the "View Sample Test" button.	A sample test is displayed to the user.	A sample test is succesfully displayed to the user.	PASS	Koushik Raju
TC_A/B Test_07	Verify the user can navigate back from the A/B test creation page to the A/B Test section.	User must be logged into the website and be in the A/B Test creation page.	1. After clicking "Create A/B Test", go to the A/B test creation page. / 2. Click the back button.	User is navigated back to the A/B Test section.	User is succesfully navigated back to the A/B Test section.	PASS	Koushik Raju
TC_A/B Test_08	Verify that the user can select only one section at a time.	User must be logged into the website and in the A/B Test section.	1. Select the "Easy to Edit" section. / 2. Try to select the "Cross Platform Testing" section.	The previous section should be deselected when a new one is selected.	The previous section is deselected when a new one is selected.	PASS	Koushik Raju
TC_A/B Test_09	Verify that the user can cancel or close the sample test view.	User must be logged into the website and in the A/B Test section with any section selected.	1. Click on "View Sample Test". / 2. Close or cancel the sample test view.	The sample test view should close, and the user should be back in the A/B Test section.	Sample test view is clossed and webpage is returned back to A/B test section	PASS	Koushik Raju	BUG detected : When the page is returned back ro A/B Section the icon is seperated from the A/B Test word. / After trying multiple itteration the problem occurs constantly.
TC_A/B Test_10	Verify that "Create A/B Test" button is disabled if no sections are selected.	User must be logged into the website and in the A/B Test section, and no section should be selected.	1. Ensure no section is selected. / 2. Verify that "Create A/B Test" is disabled.	The "Create A/B Test" button should be disabled when no section is selected.	"Create A/B Test" button is disabled when no section is selected.	PASS	Koushik Raju
TC_A/B Test_11	Verify the UI layout of the A/B Test section is responsive across different devices.	User must be logged into the website and in the A/B Test section on a mobile, tablet, or desktop device.	Open the A/B Test section on different devices (mobile, tablet, desktop).	The A/B Test section should be displayed properly on all devices without any UI issues.	The webpage does not render properly on mobuile platform.	FAIL	Koushik Raju	Webpage A/B Test is succesfully loaded in desktop, tablet browsers. / But in mobile browser the all the elements in the webpage is collapsed. / This problem is constant even after multiple attempst of reloding and is the same in various browsing apps. I used Safari, Chrome, Brave apps.
TC_A/B Test_12	Verify that the user can successfully logout after using the A/B Test section.	User must be logged into the website and in the A/B Test section.	1. Navigate to the A/B Test section. / 2. Click on the logout button.	User should be logged out successfully and redirected to the login page.	User is succesfullty loged out and redirected to login page.	PASS	Koushik Raju
TC_A/B Test_13	Verify that the A/B Test section loads within 5 seconds.	User must be logged into the website.	1. Click on the A/B Test icon. / 2. Measure the time taken for the section to fully load.	The A/B Test section should fully load within 5 seconds.	I tried more that 20 itterations each time the webpage renders within 5 sec.	PASS	Koushik Raju
TC_A/B Test_14	Verify that a user can cancel the creation of an A/B test and return to the A/B Test section.	User must be logged into the website and in the A/B Test section with a section selected.	1. Select any section. / 2. Click on "Create A/B Test". / 3. Click on the "Cancel" button or close the creation page.	The user should be redirected back to the A/B Test section without any changes made to the test creation.	The user is successfully redirected back to the A/B Test section without any changes made to the test creation.	PASS	Koushik Raju
TC_A/B Test_15	Verify that "View Sample Test" displays a summary of the test configuration.	User must be logged into the website and in the A/B Test section with a section selected.	1. Select a section. / 2. Click "View Sample Test".	The sample test summary should display the configuration for the selected section.	The sample test summary is displayes the configuration for the selected section.	PASS	Koushik Raju