## TaskPage
Test Plan for VWO Dashboard Section
Test Execution Start Date : 01-04-2025
Test Execution End Date : 28-04-2025
Test Executionar : Koushik Raju

1. Introduction
The VWO Dashboard Section Test Plan outlines the functional testing approach for ensuring that all dashboard components, including Active Tests, Untested Hypotheses, Rolled-out Experience, and Total Experience Bar, work as expected. The goal is to verify that the dashboard is accessible, displays correct data, and provides a seamless user experience.

2. Test Objective
The primary objective is to validate the functionality, navigation, UI responsiveness, and performance of the dashboard section to ensure it meets user requirements and business needs.tests, view sample tests, and navigate smoothly within the portal.

3. Scope of Testing
The scope of testing will include the following: / *UI and navigation testing for all dashboard sections. / *Validation of dashboard filters, sorting, and search. / *Data accuracy in graphs, charts, and experience reports. / *Performance testing for page load and data refresh.

4. Number of Test Cases = 15

5. Test Type
Functional Testing, UI Testing, Usability Testing, Error Handling

6.Test Assumptions
*The user has a valid VWO login account. / *The test environment is stable and accessible. / *Test data (active tests, hypotheses, rolled-out experiences) is available for validation.

7.Pass/Fail Criteria
A test case will pass if the expected result matches the actual result. A test case will fail if there is a deviation.

## TeseCase_Details
Test Case Details

Test Execution Start Date : 01-04-2025
Test Execution End Date : 28-04-2025
Test Executionar : Koushik Raju

	Test case No	Test Case Description	Priority	Pre Condition	Status
	TC_Dashboard_01	Verify Successful Login and Dashboard Access	HIGH	1. app.vwo.com Page is loaded. / 2. User has a registered account.	Pending
	TC_Dashboard_02	Verify Dashboard UI Elements Load Correctly	HIGH	1. app.vwo.com Page is loaded. / 2. User has a registered account.	Pending
	TC_Dashboard_03	Verify Dashboard UI Elements fucntion load properly	MEDIUM	1. app.vwo.com Page is loaded. / 2. User has a registered account.	Pending
	TC_Dashboard_04	Verify Dashboard Filters Work as Expected	HIGH	User has multiple test campaigns/reports.	Pending
	TC_Dashboard_05	Verify Dashboard Responsiveness on Different Devices	HIGH	1. app.vwo.com Page is loaded. / 2. User has a registered account.	Pending
	TC_Dashboard_06	Verify Notifications and Alerts on Dashboard	HIGH	User has active campaigns or alerts enabled.	Pending
	TC_Dashboard_07	Verify User Session Timeout Handling	HIGH	User is logged in and inactive.	Pending
	TC_Dashboard_08	Verify Navigation Between Dashboard Sections	HIGH	User is logged in and located in Dashboard page.	Pending
	TC_Dashboard_09	Verify Navigation to Active Tests Section	HIGH	User is logged in and located in Dashboard page.	Pending
	TC_Dashboard_10	Verify Navigation to Untested Hypotheses Section	HIGH	User is logged in and located in Dashboard page.	Pending
	TC_Dashboard_11	Verify Navigation to Rolled-out Experience Section	HIGH	User is logged in and located in Dashboard page.	Pending
	TC_Dashboard_12	Verify Sorting Functionality in Active Tests Section	HIGH	1.User is logged in and located in Dashboard page. / 2.User has multiple active tests.	Pending
	TC_Dashboard_13	Verify Dashboard Data Auto-Refresh	LOW	User has active campaigns with real-time data.	Pending
	TC_Dashboard_14	Verify Dashboard Data Auto-Refresh across diferent devices	HIGH	1. app.vwo.com Page is loaded. / 2. User has a registered account.	Pending
	TC_Dashboard_15	Verify if Dashboard elements adjust accordingly when browser size Is changed.	HIGH	1.User is logged in and located in Dashboard page. / 2.User has multiple active tests.	Pending

## Test_Execution&Results
Test case No	Test Case Title	Pre Condition	Steps to Execute	Expected Result	Actual Result	Status	Executed QA Name	Misc (Comments)
TC_Dashboard_01	Verify Successful Login and Dashboard Access	1. app.vwo.com Page is loaded. / 2. User has a registered account.	1. Open app.vwo.com / 2. Enter valid credentials, user name - kawogi6948@oronny.com, pass - Kawogi@12345 / 3. Click "Login" / 4. Observe if the dashboard loads.	The user should be redirected to the dashboard without errors.	The page was logined and redirected to dashboard section when clicked.	PASS	Koushik Raju
TC_Dashboard_02	Verify Dashboard UI Elements Load Correctly	1. app.vwo.com Page is loaded. / 2. User has a registered account.	1. Navigate to the dashboard. / 2. Verify the presence of navigation bar, graphs, recent activities, etc.	All elements should be visible and correctly positioned.	All elements in dashboard are visible properly	PASS	Koushik Raju
TC_Dashboard_03	Verify Dashboard UI Elements fucntion load properly	1. app.vwo.com Page is loaded. / 2. User has a registered account.	1. Navigate to the dashboard. / 2. Verify the presence of Active test bar, Untested hypotheses bar, Rolled oput experience bar, Total experience bar.	Active test bar, Untested hypotheses bar, Rolled oput experience bar, Total experience bar should load their appropriate functions when clicke on it.	All elements in dashboard functions properly when clicked.	PASS	Koushik Raju
TC_Dashboard_04	Verify Dashboard Filters Work as Expected	User has multiple test campaigns/reports.	1. Apply different filters (Date, Status, Type). / 2. Observe if displayed data updates.	The applied filters should correctly refine the displayed data.	The applied filters correctly refine the displayed data.	PASS	Koushik Raju
TC_Dashboard_05	Verify Dashboard Responsiveness on Different Devices	1. app.vwo.com Page is loaded. / 2. User has a registered account.	1. Open dashboard on Desktop, Tablet, and Mobile. / 2. Check UI elements for alignment.	The layout should be responsive without distortion.	The responce in desktop and tablet loads properly but in mobile dashboard does not render at all.	FAIL	Koushik Raju	Only in mobile browser the webpage is not rendered succesfully.It keeps on loading forever. I used CHROME, BRAVE apps in mobile testing.
TC_Dashboard_06	Verify Notifications and Alerts on Dashboard	User has active campaigns or alerts enabled.	1. Trigger an alert when campaign completion. / 2. Check if a notification appears.	The notification should be displayed with accurate information.	When campai completion, a notifiaction apperas succesfull	PASS	Koushik Raju
TC_Dashboard_07	Verify User Session Timeout Handling	User is logged in and inactive.	1. Stay inactive for 15-30 minutes. / 2. Try performing an action.	The user should be logged out and redirected to login.	User is logged out and redirected to login page succesfully.	PASS	Koushik Raju
TC_Dashboard_08	Verify Navigation Between Dashboard Sections	User is logged in and located in Dashboard page.	1. Click on different dashboard sections. / 2. Observe navigation speed and behavior.	Navigation should be smooth with no broken links.	Navigation is smooth with no broken links.	PASS	Koushik Raju
TC_Dashboard_09	Verify Navigation to Active Tests Section	User is logged in and located in Dashboard page.	1. Click on the Active Tests section. / 2. Observe if the section loads correctly.	The Active Tests section should open without delay or errors.	The Active Tests section is open without delay or errors.	PASS	Koushik Raju
TC_Dashboard_10	Verify Navigation to Untested Hypotheses Section	User is logged in and located in Dashboard page.	1. Click on the Untested Hypotheses section. / 2. Observe if the section loads correctly.	The Untested Hypotheses section should open without issues.	The Untested Hypotheses is hould open without issues.	PASS	Koushik Raju
TC_Dashboard_11	Verify Navigation to Rolled-out Experience Section	User is logged in and located in Dashboard page.	1. Click on the Rolled-out Experience section. / 2. Observe if the section loads correctly.	The Rolled-out Experience section should be accessible without delay.	The Rolled-out Experience section is accessible without delay.	FAIL	Koushik Raju	After trying more than 10 itterations, each time there is dealy of about average 20 sec to load the Rolled-Out experience section .
TC_Dashboard_12	Verify Sorting Functionality in Active Tests Section	1.User is logged in and located in Dashboard page. / 2.User has multiple active tests.	1. Navigate to Active Tests. / 2. Apply different sorting options (e.g., by date, status).	The tests should be sorted correctly based on the selected criteria.	The tests are correctly based on the selected criteria.	PASS	Koushik Raju	I sorted the test cases bades on date and completed status.
TC_Dashboard_13	Verify Dashboard Data Auto-Refresh	User has active campaigns with real-time data.	1. Monitor an active test campaign. / 2. Check if data refreshes without manual intervention.	Dashboard should auto-refresh and display real-time updates.	Dashboard is auto refreshed and real time updates are displayed.	PASS	Koushik Raju
TC_Dashboard_14	Verify Dashboard Data Auto-Refresh across diferent devices	1. app.vwo.com Page is loaded. / 2. User has a registered account.	1. Open dashboard on Desktop, Tablet, and Mobile. / 2. Check UI elements for alignment.	The layout should be responsive without distortion.	The layout in desktop and tablet loads properly by in mobile the UI elements are disordered	FAIL	Koushik Raju	Only in mobile browser the webpage is not rendered succesfully. I used CHROME, BRAVE, BING browsers.
TC_Dashboard_15	Verify if Dashboard elements adjust accordingly when browser size Is changed.	1.User is logged in and located in Dashboard page. / 2.User has multiple active tests.	1. Open dashboard on desktop browser. / 2. Alter the size of browser on your fee will.	The dashboard page and its elements should adjust accordingly withous and break or overlaping of sections and its respective data.	When browser size is changed the Dashboard elemets change accordingly. All its corresponding datas also change accordinglhy.	PASS	Koushik Raju